## Plan
Channel Strategy, Selection, and Management Plan
Project Information | [6 empty] | Gantt Chart (End of Week)
ID | Project Name | Owner | Budget | Duration | Start | End | 2004-07-09 | 2004-07-16 | 2004-07-23 | 2004-07-30 | 2004-08-06 | 2004-08-13 | 2004-08-20 | Status
1 | Channel Strategy, Selection, and Management Plan | R. Ihrig | 95600 | 33 days | 2004-07-05 08:00 | 2004-08-18 17:00
| Planned (to date): |  | 85200 | 30 | 2004-07-05 | 2004-08-13
| Actual (to date): |  | 89000 | 30 | Actual
| Variance: |  | -3800 | 0 |  |  | Comments: Provide comments on overall health of the project.
Dependencies on:
Dependencies for:
ID | Deliverable Name/Task Name | Assigned To | Cost | Duration | Start | End | 2004-07-09 | 2004-07-16 | 2004-07-23 | 2004-07-30 | 2004-08-06 | 2004-08-13 | 2004-08-20 | Status
1.1 | Channel Strategy | R. Ihrig | 4800 | 5 days | 2004-07-05 08:00 | 2004-07-09 17:00
1.1.1 | Define objectives | R. Ihrig | 800 | 0.5 days | 2004-07-05 08:00 | 2004-07-05 12:00
1.1.2 | Develop channel schema | S. Abbas | 800 | 1 day | 2004-07-05 13:00 | 2004-07-06 12:00
1.1.3 | Assess channel pros and cons | S. Abbas | 2400 | 3 days | 2004-07-06 13:00 | 2004-07-09 12:00
1.1.4 | Determine channel alignment with objectives | R. Ihrig | 800 | 0.5 days | 2004-07-09 13:00 | 2004-07-09 17:00
Summary
| Planned (to date): |  | 4800 | 5 | 2004-07-05 | 2004-07-09 | Comments: Provide comments.
| Actual (to date): |  | 6000 | 5 | Actual
| Variance: |  | -1200 | 0
Dependencies on:
Dependencies for:
Comments:
ID | Deliverable Name/Task Name | Assigned To | Cost | Duration | Start | End | 2004-07-09 | 2004-07-16 | 2004-07-23 | 2004-07-30 | 2004-08-06 | 2004-08-13 | 2004-08-20 | Status
1.2 | Channel Plan | D. Daniels | 24000 | 7 days | 2004-07-12 08:00 | 2004-07-20 17:00
1.2.1 | Develop channel tactical calendar | B. Gage | 1200 | 1 day | 2004-07-12 08:00 | 2004-07-12 17:00
1.2.2 | Develop high-level positioning for preferred channel type | R. Ihrig | 1600 | 1 day | 2004-07-12 08:00 | 2004-07-12 17:00
1.2.3 | Develop pricing, discounts, and promotion guidelines | R. Ihrig, D. Daniels, S. Abbas | 8800 | 2 days | 2004-07-13 08:00 | 2004-07-14 17:00
1.2.4 | Define channel functions | D. Daniels | 4000 | 2 days | 2004-07-15 08:00 | 2004-07-16 17:00
1.2.5 | Develop a budget for overall channel management | B. Gage, R. Ihrig, D. Daniels, S. Abbas | 5600 | 1 day | 2004-07-19 08:00 | 2004-07-19 17:00
1.2.6 | Develop channel plan | S. Abbas, D. Daniels | 2800 | 1 day | 2004-07-20 08:00 | 2004-07-20 17:00
Summary
| Planned (to date): |  | 24000 | 7 | 2004-07-12 | 2004-07-20 | Comments: Provide comments.
| Actual (to date): |  | 25400 | 7 | Actual
| Variance: |  | -1400 | 0
Dependencies on:
Dependencies for:
ID | Deliverable Name/Task Name | Assigned To | Cost | Duration | Start | End | 2004-07-09 | 2004-07-16 | 2004-07-23 | 2004-07-30 | 2004-08-06 | 2004-08-13 | 2004-08-20 | Status
1.3 | Channel Selection | R. Ihrig | 42400 | 13 days | 2004-07-21 08:00 | 2004-08-06 17:00
1.3.1 | Develop channel partner selection criteria | R. Ihrig, D. Daniels | 3600 | 1 day | 2004-07-21 08:00 | 2004-07-21 17:00
1.3.2 | Create a channel selection matrix | D. Daniels, S. Abbas | 5600 | 2 days | 2004-07-22 08:00 | 2004-07-23 17:00
1.3.3 | Identify target channel partners | R. Ihrig, D. Daniels, S. Abbas | 13200 | 3 days | 2004-07-26 08:00 | 2004-07-28 17:00
1.3.4 | Develop channel partners profile | D. Daniels, S. Abbas | 5600 | 2 days | 2004-07-29 08:00 | 2004-07-30 17:00
1.3.5 | Determine contractual terms | R. Ihrig, S. Ito | 6400 | 2 days | 2004-08-02 08:00 | 2004-08-03 17:00
1.3.6 | Negotiate contract | R. Ihrig, S. Ito | 6400 | 2 days | 2004-08-04 08:00 | 2004-08-05 17:00
1.3.7 | Sign off on contract | R. Ihrig | 1600 | 1 day | 2004-08-06 08:00 | 2004-08-06 17:00
Summary
| Planned (to date): |  | 42400 | 13 | 2004-07-21 | 2004-08-06 | Comments: Provide comments.
| Actual (to date): |  | 43000 | 13 | Actual
| Variance: |  | -600 | 0
Dependencies on:
Dependencies for:
ID | Deliverable Name/Task Name | Assigned To | Cost | Duration | Start | End | 2004-07-09 | 2004-07-16 | 2004-07-23 | 2004-07-30 | 2004-08-06 | 2004-08-13 | 2004-08-20 | Status
1.4 | Channel Management | R. Ihrig | 24400 | 8 days | 2004-08-09 08:00 | 2004-08-18 17:00
1.4.1 | Define training needs | S. Abbas, D. Daniels | 2800 | 1 day | 2004-08-09 08:00 | 2004-08-09 17:00
1.4.2 | Define promotion needs | D. Daniels, R. Ihrig | 7200 | 2 days | 2004-08-10 08:00 | 2004-08-11 17:00
1.4.3 | Develop timing requirements and budget | R. Ihrig, B. Gage | 2800 | 1 day | 2004-08-12 08:00 | 2004-08-12 17:00
1.4.4 | Develop a channel communication plan | B. Gage | 1200 | 1 day | 2004-08-13 08:00 | 2004-08-13 17:00
1.4.5 | Determine channel performance criteria | R. Ihrig | 1600 | 1 day | 2004-08-16 08:00 | 2004-08-16 17:00
1.4.6 | Develop channel marketing management plan | D. Daniels, S. Abbas, R. Ihrig | 8800 | 2 days | 2004-08-17 08:00 | 2004-08-18 17:00
Summary
| Planned (to date): |  | 14000 | 5 | 2004-08-09 | today | Comments: Provide comments.
| Actual (to date): |  | 14600 | 5 | Actual
| Variance: |  | -600 | 0
Dependencies on:
Dependencies for:
Planned
Planned to date
Actual